## Overview
DecVAE baseline experiments: planner
One row per method and dataset on the Runs sheet. Counts below update from the Status column there.
Run status
Status | Runs
Not started | 15
Queued | 0
Running | 0
Done | 1
Failed | 0
Optional | 7
Dropped | 0
Total runs | 24
Effort
Runs needing pre-training | 14
Runs with no GPU cost | 9
Estimated GPU hours (total) | 12
Estimated GPU hours remaining | 0
Evaluations completed | 1
Legend
Yellow cells are the ones to fill in: Est. GPU h, Started, Finished, Checkpoint and W&B on the Runs sheet; the baseline column on Protocol; every metric on Results. Days is a formula and fills itself once both dates are entered. Status and Eval done are dropdowns. Estimated GPU hours are deliberately left blank rather than guessed, except for the inference-only rows where the true cost is zero.
Sequencing
Ranks 1 and 2 (wav2vec2, SFA) need no GPU and can proceed immediately alongside everything else. Among the GPU jobs run CoST first: it is the most direct competitor to the central claim, so an adverse result is worth discovering early. Ranks 1 to 7 are the defensible minimum and close every baseline request made by name. Ranks 8 and 9 strengthen the paper beyond compliance.

## Runs
Baseline runs: one row per method and dataset
Yellow cells are for you to fill in. Ranks follow the agreed priority order. Delete the EXAMPLE row.
Run ID | Rank | Method | Family | Dataset | Branches | Latent dim | Pre-train | Est. GPU h | Status | Started | Finished | Days | Checkpoint | W&B run | Eval done | Notes
EXAMPLE | 0 | (delete this row) | - | TIMIT | Z + S | 64 | Yes | 12 | Done | 2026-09-15 | 2026-09-16 | 1 | ckpt/example | wandb/abc123 | Yes | Shows the expected format
W2V-SIM | 1 | wav2vec2 (frozen) | Speech SSL | SimVowels | Z | 64 | No | 0 | Not started | [5 empty] | No | Inference only. Same encoder family as DecVAE
W2V-TIM | 1 | wav2vec2 (frozen) | Speech SSL | TIMIT | Z | 64 | No | 0 | Not started | [5 empty] | No | Inference only
W2V-IEM | 1 | wav2vec2 (frozen) | Speech SSL | IEMOCAP | Z + S | 64 | No | 0 | Not started | [5 empty] | No | Inference only
WLM-SIM | 1 | WavLM (frozen) | Speech SSL | SimVowels | Z | 64 | No | 0 | Optional | [5 empty] | No | Optional modern alternative to wav2vec2, same zero cost
WLM-TIM | 1 | WavLM (frozen) | Speech SSL | TIMIT | Z | 64 | No | 0 | Optional | [5 empty] | No | Optional
WLM-IEM | 1 | WavLM (frozen) | Speech SSL | IEMOCAP | Z + S | 64 | No | 0 | Optional | [5 empty] | No | Optional
SFA-SIM | 2 | SFA | Slowness | SimVowels | Z + S | 48 | No | 0 | Not started | [5 empty] | No | sklearn-sfa. Run at 20 comps (to match PCA/ICA) and at z_dim
SFA-TIM | 2 | SFA | Slowness | TIMIT | Z + S | 64 | No | 0 | Not started | [5 empty] | No | Needs ordered contiguous frames. Use context stacking or quadratic expansion
SFA-IEM | 2 | SFA | Slowness | IEMOCAP | Z + S | 64 | No | 0 | Not started | [5 empty] | No
COST-SIM | 3 | CoST | Decomposition | SimVowels | Z | 48 | Yes |  | Not started | [5 empty] | No | RUN THIS FIRST of the GPU jobs: most dangerous comparison
COST-TIM | 3 | CoST | Decomposition | TIMIT | Z | 64 | Yes |  | Not started | [5 empty] | No | Apply at utterance level over Mel frames, closer to its intended use
TCL-SIM | 4 | TCL | Time-contrastive | SimVowels | Z | 48 | Yes |  | Not started | [5 empty] | No | Segment-index pretext. Decide segment definition (uniform time bins within utterance)
TCL-TIM | 4 | TCL | Time-contrastive | TIMIT | Z | 64 | Yes |  | Not started | [5 empty] | No | Small MLP; cheapest neural baseline
FHV-SIM | 5 | FHVAE | Sequential VAE | SimVowels | Z + S | 48 | Yes |  | Not started | [5 empty] | No | Two-timescale, directly comparable to the S/Z branches
FHV-TIM | 5 | FHVAE | Sequential VAE | TIMIT | Z + S | 64 | Yes |  | Not started | [5 empty] | No | Originally evaluated on TIMIT: zero protocol invention
CPC-TIM | 6 | CPC | Sequential SSL | TIMIT | Z | 64 | Yes |  | Not started | [5 empty] | No | Named explicitly by R5. TIMIT only, coverage tier
CF-IEM-1 | 7 | (carry-forward #1, TBD) | TBD | IEMOCAP | Z + S | 64 | Yes |  | Not started | [5 empty] | No | Best of CoST / TCL / FHVAE. Fine-tuning protocol as for DecVAE
CF-IEM-2 | 7 | (carry-forward #2, TBD) | TBD | IEMOCAP | Z + S | 64 | Yes |  | Not started | [5 empty] | No | Second best. Hardest case for the frequency prior
TFC-SIM | 8 | TF-C | Time-frequency SSL | SimVowels | Z | 48 | Yes |  | Optional | [5 empty] | No | Sharpest test: one frequency view vs C orthogonal components
TFC-TIM | 8 | TF-C | Time-frequency SSL | TIMIT | Z | 64 | Yes |  | Optional | [5 empty] | No | Public code organised around pre-train then transfer
SLV-SIM | 9 | SlowVAE | Slowness / temporal sparsity | SimVowels | Z | 48 | Yes |  | Optional | [5 empty] | No | SimVowels first: identifiability claim needs ground-truth factors
SLV-TIM | 9 | SlowVAE | Slowness / temporal sparsity | TIMIT | Z | 64 | Yes |  | Optional | [5 empty] | No | Only if budget allows

## Methods
Method reference table
Status column: Benchmark, Optional, Dropped, or Cite and distinguish. Filter on it to see the benchmark set.
Method | Family | Source | Code | Unsupervised | Emits embedding | Requested by | Decision | Adaptation needed | Notes and risks
CoST | Decomposition-based representation learning | Woo et al., ICLR 2022 | arxiv.org/abs/2202.01575 | Yes | Yes | R3 #1, R5 #2 | Benchmark | Apply at utterance level over Mel frames; match z_dim | Built for forecasting; seasonal/trend split may be degenerate on 25 ms frames
TCL | Time-contrastive learning / nonlinear ICA | Hyvarinen & Morioka, NeurIPS 2016 | - | Yes | Yes | R1 #5, R3 #1 | Benchmark | MLP on Mel frames, segment index as pretext label | Segment definition matters; use uniform time bins within utterance
FHVAE | Disentangled sequential VAE | Hsu, Zhang & Glass, NeurIPS 2017 (ref [16]) | - | Yes | Yes | R1 #5, R5 #2 | Benchmark | None: originally evaluated on TIMIT with the same two-timescale structure | Safest baseline. Already cited in the manuscript
TF-C | Self-supervised time-frequency consistency | Zhang et al., NeurIPS 2022 | github.com/mims-harvard/TFC-pretraining | Yes | Yes | R5 #2 | Benchmark (optional) | Feed Mel frames; keep their pre-train/fine-tune split | Its time-vs-frequency alignment is the single-view special case of L_recon
CPC | Contrastive predictive coding | van den Oord et al., 2018 (ref [2]) | - | Yes | Yes | R5 #2 | Benchmark | Standard InfoNCE with autoregressive context on Mel frames | Cited already, but currently mis-cited at main line 29; move it
wav2vec2 | Self-supervised speech representation | Baevski et al., NeurIPS 2020 (ref [40]) | HuggingFace checkpoint | Yes | Yes | R5 #2 | Benchmark | Frozen; extract embeddings only | Zero pre-training cost. DecVAE's encoder is already Wav2Vec2-based
WavLM | Self-supervised speech representation | Chen et al., 2022 | HuggingFace checkpoint | Yes | Yes | R5 #2 (implied) | Optional | Frozen; extract embeddings only | Same slot as wav2vec2, same zero cost; more current for speaker and emotion tasks
SFA | Slow feature analysis | Wiskott & Sejnowski, Neural Computation 2002 | github.com/wiskott-lab/sklearn-sfa | Yes | Yes | R1 #5 | Benchmark | Whiten, then PCA on time derivatives, smallest eigenvalues | Needs ordered contiguous frames. Use nonlinear expansion so it is not handicapped
SlowVAE | Temporal sparse coding, slowness prior | Klindt et al., ICLR 2021 | github.com/bethgelab/slow_disentanglement | Yes | Yes | R1 #5 (recent reading) | Benchmark (optional) | Matched encoder and z_dim | Answers the word 'recent' in R1's comment, which classical SFA does not
DSVAE | Disentangled sequential autoencoder | Li & Mandt, ICML 2018 | - | Yes | Yes | R5 #2 | Dropped | Static/dynamic split would need adapting from video to speech | Same reviewer slot as FHVAE, more protocol invention. First to cut
BTSF | Unsupervised temporal-spectral fusion | Yang & Hong, ICML 2022 | proceedings.mlr.press/v162/yang22e.html | Yes | Yes | R5 #2 | Dropped | Instance-level embedding, drops into the eval pipeline | Passes the filter but the comparison is less pointed than TF-C
LaST | Variational seasonal-trend latent decomposition | Wang et al., NeurIPS 2022 | github.com/zhycs/LaST | No (needs forecasting targets) | Yes | R5 #2 | Cite and distinguish | Not benchmarkable without inventing a proxy task | CLOSEST prior work to VDA: variational latent decomposition with MI-based independence. Must be cited
Autoformer | Forecasting with decomposition blocks | Wu et al., NeurIPS 2021 | - | No | No | R5 #2 | Cite and distinguish | n/a | Not currently cited anywhere in the manuscript. Add it
FEDformer | Forecasting with frequency-enhanced decomposition | Zhou et al., ICML 2022 (ref [38]) | - | No | No | R5 #2 | Cite and distinguish | n/a | Already cited as [38]. Expand the discussion of why it is not a baseline
SpeechSplit | Unsupervised speech decomposition | Qian et al., ICML 2020 | github.com/auspicious3000/SpeechSplit | Yes | Yes | - | Cite (decision D4) | Needs an F0 stream; bottleneck tuning is fragile | Speech-native decomposition competitor. Contingency if TIMIT or IEMOCAP come out close

## Protocol
Matched protocol checklist
Fill the baseline column as each method is set up. Any unmatched row must be disclosed in the response letter.
Protocol dimension | DecVAE value | Baseline value | Matched? | Notes
Input features | Mel filterbank, 80 bands |  |  | Supp. Table 5. Must be identical for every baseline
Max / min duration | 4 s (sim), 7.15 s (real) / 1 s |  |  | Supp. Table 5
Latent dimensionality | 48 (sim), 64 (real) per subspace |  |  | PCA/ICA use 20; run SFA at both to pre-empt the asymmetry question
Aggregation | Concatenation of original + component subspaces |  |  | Not applicable to single-subspace baselines; note this
Parameter budget |  |  |  | Record encoder parameter counts so the letter can claim rough matching
Optimizer | Adam (b1 0.5, b2 0.999, eps 1e-6, wd 1e-4) |  |  | Supp. Table 5
Learning schedule | Constant with warmup (Z), linear (S) |  |  | Peak 8e-5 (Z), 1e-4 (S)
Early stopping | delta 0.2%, patience 5, warmup 100 epochs |  |  | Supp. Table 5
Downstream classifiers | LogReg, Random Forest, SVM |  |  | Deliberately simple, to expose representation quality
Cross-validation | 5-fold outer, 3-fold inner, 5 seeds |  |  | LOSO on IEMOCAP with 10 seeds
Disentanglement metrics | MI, GCN, DCI (D/C/I), Modularity, Explicitness, IRS |  |  | All take (embedding, factor label) arrays: no code changes needed
Confidence intervals | 95% over folds and seeds
Frame ordering | Random masking of l_SSL% of frames |  |  | SFA REQUIRES ordered contiguous frames: check the collator path

## Results
Results grid, to fill as runs complete
Task A/B/C by dataset. SimVowels: vowel, speaker. TIMIT: phoneme, speaker. IEMOCAP: emotion, speaker, phoneme.
Method | Dataset | MI | GCN | DCI-D | DCI-C | DCI-I | Modularity | Explicitness | IRS | Task A | Task B | Task C | Notes
DecVAE (best variant) | SimVowels | [11 empty] | Existing result: copy from Supp. Tables
DecVAE (best variant) | TIMIT | [11 empty] | Existing result: copy from Supp. Tables
DecVAE (best variant) | IEMOCAP | [11 empty] | Existing result: copy from Supp. Tables
DecAE (beta = 0) | SimVowels | [11 empty] | Existing result: copy from Supp. Tables
beta-VAE | SimVowels | [11 empty] | Existing result: copy from Supp. Tables
beta-VAE | TIMIT | [11 empty] | Existing result: copy from Supp. Tables
beta-VAE | IEMOCAP | [11 empty] | Existing result: copy from Supp. Tables
PCA | SimVowels | [11 empty] | Existing result: copy from Supp. Tables
ICA | SimVowels | [11 empty] | Existing result: copy from Supp. Tables
wav2vec2 (frozen) | SimVowels | [11 empty] | New
wav2vec2 (frozen) | TIMIT | [11 empty] | New
wav2vec2 (frozen) | IEMOCAP | [11 empty] | New
SFA | SimVowels | [11 empty] | New
SFA | TIMIT | [11 empty] | New
SFA | IEMOCAP | [11 empty] | New
CoST | SimVowels | [11 empty] | New
CoST | TIMIT | [11 empty] | New
TCL | SimVowels | [11 empty] | New
TCL | TIMIT | [11 empty] | New
FHVAE | SimVowels | [11 empty] | New
FHVAE | TIMIT | [11 empty] | New
CPC | TIMIT | [11 empty] | New
TF-C | SimVowels | [11 empty] | New
TF-C | TIMIT | [11 empty] | New
SlowVAE | SimVowels | [11 empty] | New
(carry-forward #1) | IEMOCAP | [11 empty] | New
(carry-forward #2) | IEMOCAP | [11 empty] | New