## Overview
DecVAE revision tracker
npj Artificial Intelligence, submission c86c5415-7be3-43e1-8a57-9b3e782755ae
Update the Status column on each sheet. The counts below follow automatically.
Reviewer comments
Status | Count
Not started | 21
Planned | 0
In progress | 12
Blocked | 1
Done | 2
Dropped | 0
Optional | 0
Total | 36
Experiments and analyses
Status | Count
Not started | 8
Planned | 7
In progress | 0
Blocked | 0
Done | 0
Dropped | 2
Optional | 2
Total | 19
Writing tasks
Status | Count
Not started | 22
Planned | 0
In progress | 2
Blocked | 2
Done | 0
Dropped | 0
Optional | 0
Total | 26
Open decisions
Status | Count
Not started | 0
Planned | 0
In progress | 0
Blocked | 7
Done | 0
Dropped | 0
Optional | 0
Total | 7
Key sequencing note
Experiment ranks 1 and 2 need no GPU and can run alongside everything else. Among the GPU jobs, run CoST first: it is the most dangerous comparison, so the result is worth having early. Ranks 1 to 7 are the defensible minimum and close every named baseline request. Ranks 8 and 9 make the paper stronger rather than merely compliant.

## Comments
Reviewer comments (35 comments + editor)
ID | Reviewer | Severity | Comment | Type | Master response | Status | Priority | Notes
Editor | Editor | - | Four themes: framing, baselines, disentanglement evidence, presentation | Umbrella | MR-A/B/D | In progress | High | Cover letter drafted
R1 #1 | R1 | Minor | Autoencoder naming: relabel or rename | Text | MR-A | In progress | High | Adopting R1's relabel option; keep DecVAE. Do NOT use the PCA/ICA precedent argument
R1 #2 | R1 | Minor | Discuss compactness and deployment trade-off | Text | - | Not started | Medium | Quantify dimensionality vs VAE baselines
R1 #3 | R1 | Minor | Intuition for adversarial stabilisation in main text | Text | MR-B | Not started | Medium | Consider adding KL collapse curves
R1 #4 | R1 | Minor | Notation mapping table, main vs supplement | Text | - | Not started | Medium | Z-tilde / z_c-tilde vs h_i / Z^k, and h = w^-1(z)
R1 #5 | R1 | Major | Sequence-based or contrastive baselines | Experiment | MR-D | In progress | High | Covered by TCL, SFA, SlowVAE, FHVAE
R1 #6 | R1 | - | Beta sensitivity vs orthogonality and accuracy | Analysis | - | Not started | Medium | Beta curve with accuracy and GCN at the same time
R2 | R2 | Minor | Proofread; expand figure captions | Text | - | Not started | Low | Figs 1, 2, 6 most likely
R3 #1 | R3 | Major | TCL and CoST in at least one task | Experiment | MR-D | In progress | High | Running on two datasets, not one
R3 #2 | R3 | Major | FD fixed frequency boundaries and generalisability | Text | MR-E | Not started | High | Position: boundaries are a per-signal-class hyperparameter
R3 #3 | R3 | Minor | Unresolved citation, line 499 | Text | - | Done | Low | Resolves correctly in current draft; reviewer saw an earlier compile
R3 #4 | R3 | Minor | Missing space, line 508 | Text | - | In progress | Low | Also line 736 ('Alg. 1and'); full sweep pending
R4 #1 | R4 | Major/Minor | Decomposition is an inductive bias, not a guarantee | Text / Experiment | MR-E | Not started | High | Aligns with our own view; state when it helps. We can argue that even when semantic factors are split across components, their combination achieves disentanglement. This could be set up as an experiment to show how emotion is distributed in VAEs vs DecVAEs (partially shown in the interpretability analysis with 3D contours)
R4 #2 | R4 | Major | Number of components under-justified | Experiment | MR-E | Not started | High | Sensitivity analysis rather than a selection rule
R4 #3 | R4 | Major | Subspace-wise evidence for interpretability | Experiment | MR-E | Not started | High | Selective prediction, leave-one-subspace-out, swapping
R4 #4 | R4 | Minor | Be precise about what orthogonality means | Text | MR-B | Not started | Medium | It is distributional separation; say so
R4 #5 | R4 | Major | Strict lower bound or DELBO-inspired objective | Text | MR-B | In progress | High | Conceding: no bound is possible, structural reason
R4 #6 | R4 | Minor | Malformed algorithm reference, page 20 | Text | - | Done | Low | Resolves in current draft; sweep still needed
R5 #1 | R5 | Minor | Encoder-only model described as a VAE | Text | MR-A | In progress | High | Same as R1 #1
R5 #2 | R5 | Major | Stronger contemporary baselines | Experiment | MR-D | In progress | High | The binding constraint on the whole baseline plan
R5 #3 | R5 | Minor | Decomposition claimed in generative process, acts as front-end | Text | MR-C | Not started | Medium | State the generative claim and the implementation separately
R5 #4 | R5 | Minor/Major | All real-world experiments are speech | Decision | - | Blocked | High | See decision D1
R5 #5 | R5 | Minor | Define or remove 'chromagram-guided dynamics' | Text | - | Not started | Low | Single occurrence, main line 92. Delete
R5 #6 | R5 | Major | SimVowels favours the decomposition prior | Experiment | MR-E | Not started | High | New synthetic data with non-frequency, mixed, correlated factors
R5 #7 | R5 | Major | Limitations of disentanglement metrics | Analysis | - | Not started | Medium | Read as: is the method ranking stable under noise and imbalance
R5 #8 | R5 | Major | Automatic or misspecified selection of C | Experiment | MR-E | Not started | High | Overlaps R4 #2
R5 #9 | R5 | Major | VOC-ALS confounds; subject-independent controls | Analysis | - | Not started | High | Where VOC-ALS effort should go, not baselines
R5 #10 | R5 | Major | IEMOCAP leave-session/speaker-out; class-wise results | Analysis | - | Not started | Medium | Session and speaker are confounded by design; say so
R5 #11 | R5 | Major | Quantify latent alignment; stability across seeds and folds | Analysis | - | Not started | Medium | Existing 5-fold x 5-seed protocol supports this
R5 #12 | R5 | Minor | Non-variational ablation of same architecture and capacity | Signpost | - | In progress | Low | DecAE (beta = 0) already reported; give table and figure numbers
R5 #13 | R5 | Major | Eqs. (4b) and (5) underdeveloped | Text | MR-C | Not started | High | Overlaps R6 #1
R5 #14 | R5 | Minor | Prove the bound or rename the objective | Text | MR-B | In progress | High | Renaming; proof is not possible
R5 #15 | R5 | Minor | Three additional citations | Text | - | Not started | Low | Assess relevance first; see decision D5
R6 #1 | R6 | Minor | Eqs. (4b), (5), (7), (9) and VAE terminology | Text | MR-A/B/C | In progress | High | Splits across three master responses
R6 #2 | R6 | Minor | Padding and random concatenation in Alg. 1 are ambiguous | Text | - | Not started | Medium | Answer the label-corruption worry specifically
R6 #3 | R6 | Major/Minor | Eq. (9) not shown to be a bound; sign conventions | Text | MR-B | In progress | High | Correct in every particular; drove the main revision

## Experiments
Experiments and analyses, in priority order
Rank | Item | Category | Datasets | GPU runs | Closes | Status | Notes
1 | wav2vec2 frozen embeddings (optionally WavLM) | Baseline | SimVowels, TIMIT, IEMOCAP | 0 (inference) | R5 #2 | Planned | Zero pre-training. Encoder is already Wav2Vec2-based, so this is a same-encoder/different-objective control
2 | Slow Feature Analysis (SFA) | Baseline | SimVowels, TIMIT, IEMOCAP | 0 (CPU) | R1 #5 | Planned | sklearn-sfa. Needs ordered contiguous frames. Use context stacking or quadratic expansion. Run at 20 comps and at z_dim
3 | CoST | Baseline | SimVowels, TIMIT | 2 | R3 #1, R5 #2 | Planned | Run first of the GPU jobs: most dangerous comparison, want the result early
4 | TCL | Baseline | SimVowels, TIMIT | 2 | R1 #5, R3 #1 | Planned | Small MLP with segment-index pretext. Best Major-comments-per-GPU-hour on the list
5 | FHVAE | Baseline | SimVowels, TIMIT | 2 | R1 #5, R5 #2 | Planned | Zero protocol invention; originally evaluated on TIMIT with the same two-timescale structure
6 | CPC | Baseline | TIMIT | 1 | R5 #2 | Planned | Named by R5 explicitly; cheap. Completes R5's five-family list
7 | IEMOCAP carry-forward (best 2 of ranks 3-5) | Baseline | IEMOCAP | 2 | R4 #1, R5 #6 | Planned | Hardest case for the frequency prior, so the most informative win
8 | TF-C | Baseline | SimVowels, TIMIT | 2 | R5 #2 | Optional | Requested by nobody but the sharpest test: one frequency view vs C orthogonal components
9 | SlowVAE | Baseline | SimVowels (TIMIT if budget) | 1-2 | R1 #5 | Optional | SimVowels first: its identifiability claim needs ground-truth factors
10 | DSVAE | Baseline | - | - | R5 #2 | Dropped | Same reviewer slot as FHVAE, more protocol invention
11 | BTSF | Baseline | - | - | R5 #2 | Dropped | Same slot as TF-C, less pointed comparison
12 | New synthetic data: non-frequency, mixed, correlated factors | Simulation | New | TBD | R5 #6, R4 #1 | Not started | Plan jointly with the baseline grid. See decision D3
13 | C sensitivity including deliberate misspecification | Ablation | SimVowels, TIMIT | TBD | R4 #2, R5 #8 | Not started | Systematic sweep rather than a selection rule
14 | Beta vs orthogonality and accuracy on common axes | Analysis | Existing runs | 0 | R1 #6 | Not started | Re-plot from existing sweeps; report D_ortho at convergence
15 | Subspace-wise: selective prediction, leave-one-out, swapping | Analysis | TIMIT, IEMOCAP | 0 | R4 #3 | Not started | Post-hoc on existing latents. Also applicable to CoST and FHVAE subspaces
16 | VOC-ALS: subject-independent, stratified, permutation tests | Analysis | VOC-ALS | 0 | R5 #9 | Not started | Where VOC-ALS effort belongs
17 | IEMOCAP class-wise results and LOSO reporting | Analysis | IEMOCAP | 0 | R5 #10 | Not started | Available from existing runs
18 | Seed and fold stability of factor alignment | Analysis | All | 0 | R5 #11 | Not started | Correlate DCI importance matrices across seeds
19 | Metric robustness under label noise and factor imbalance | Analysis | Existing latents | 0 | R5 #7 | Not started | No pre-training needed; perturb labels and re-run the metric suite

## Writing
Manuscript writing and correction tasks
ID | Task | Where | Linked to | Status | Notes
W1 | Definitional paragraph: latent-level autoencoding; rate term without sampling | Introduction + Methods | MR-A, R1 #1, R5 #1 | In progress | Draft written, needs placing and final wording
W2 | Rewrite SI Section 5: retitle, rescope, state what is and is not bounded | SI Sec. 5 | MR-B | Not started | Keep the derivation as motivation, correctly scoped
W3 | Unify sign conventions across Eq. (1), Eq. (9), SI Eq. (12), Alg. 1 | Main + SI | MR-B, R6 #3 | Not started | Code minimises L_recon + L_ortho + beta*L_prior
W4 | Separate symbols: D_recon/D_ortho for measures, L_recon/L_ortho for losses | Main + SI | MR-B, R6 #3 | Not started | This is the real source of the sign confusion
W5 | Fix SI Alg. 2 line 31: negative CE is -log(JSD), not -log(1-JSD) | SI Alg. 2 | MR-B, R6 #3 | Not started | Code uses BCE with target 1 for negatives
W6 | Withdraw the FactorVAE analogy | Main l.431, SI l.112 | MR-B | Not started | FactorVAE subtracts a term it minimises; our case is the mirror image
W7 | Rename the objective | Throughout | MR-B | Blocked | See decision D2. 'DELBO-inspired' is dropped either way
W8 | Equilibrium proposition as the positive theoretical content | SI Sec. 5 or 7 | MR-B | Not started | Replaces the lost bound; connects to the SVD/PCA argument. Decision D7
W9 | Restate Eqs. (4b), (5) and (7) | Methods | MR-C, R5 #13, R6 #1 | Not started | Marginal of a sum vs joint of independents; invalid posterior factorisation
W10 | Reconcile p(z) pushforward vs the isotropic prior; scope Assumption 1 | SI Sec. 5 | MR-C | Not started | Two different objects used interchangeably
W11 | Notation mapping table, main text vs supplement | Main + SI | R1 #4 | Not started
W12 | Remove 'chromagram-guided dynamics' | Main l.92 | R5 #5 | Not started | Single occurrence; not in SI or code
W13 | Fix spacing at lines 508 and 736; full typography sweep | Main | R3 #4 | In progress
W14 | Sweep for unresolved references and formatting artefacts | Main + SI | R3 #3, R4 #6 | Not started | Both already resolve, but state that a sweep was done
W15 | Compactness and deployment trade-off in the Discussion | Discussion | R1 #2 | Not started
W16 | Two or three sentences on adversarial stabilisation and collapse | Methods | R1 #3 | Not started
W17 | State that orthogonality here means distributional separation | Methods | R4 #4 | Not started | Cite MI and GCN results as evidence, not as construction
W18 | Signpost DecAE (beta = 0) as the non-variational ablation | Results / SI | R5 #12 | Not started | Give the specific table and figure numbers
W19 | Precise padding and random concatenation procedure | Alg. 1 | R6 #2 | Not started | Say whether concatenation is within-speaker and how labels are assigned
W20 | Assess and place the three suggested citations | Discussion | R5 #15 | Not started | See decision D5
W21 | Cite and distinguish LaST, Autoformer, FEDformer, SpeechSplit | Intro / Related work | MR-D | Not started | Autoformer is not currently cited at all; FEDformer is [38]
W22 | Move the CPC citation [2] out of the dysarthria sentence | Main l.29 | - | Not started | Currently cited as support for dysarthric speech recognition
W23 | Abstract: soften 'extends VAEs'; gloss 'encoder-only' | Abstract | MR-A | Not started | 'variational prior approximation' is already accurate; light touch only
W24 | Expand figure captions | Figs. 1, 2, 6 | R2 | Not started
W25 | Full proofreading pass | Whole manuscript | R2 | Not started
W26 | Narrow modality claims, or report the new modality | Abstract + Discussion | R5 #4 | Blocked | See decision D1

## Decisions
Open decisions (only you can settle these)
ID | Decision | Linked to | Impact | Status | Resolution
D1 | Narrow the claim to speech-like signals, or add a non-speech modality (EEG/ECG) | R5 #4, W26 | High | Blocked
D2 | Final name for the objective: redefine DELBO, or L_dec | MR-B, W7 | Medium | Blocked
D3 | Run baselines on the new synthetic dataset as well | R5 #6, MR-E, Exp 12 | High | Blocked
D4 | Benchmark SpeechSplit, or cite it only | MR-D | Low | Blocked
D5 | Are R5's three suggested citations genuinely relevant | R5 #15, W20 | Low | Blocked
D6 | Presentation of changes: tracked changes, colour, or separate marked-up file | Submission | Low | Blocked
D7 | Include the equilibrium proposition in the supplement | MR-B, W8 | Medium | Blocked